## Sheet1
Project Name | Task | Comments | Asset Tracker | Asset Tracker | Asset Tracker | Asset Tracker | Asset Tracker | Asset Tracker | Comment Fields | Tuesday | Wednesday | Thursday | Friday
|  |  | Status (Wait = W = 0% Complete) | Status (Start = S = 25% Complete) | Status (Midway = M = 50% Complete) | Status (Finishing =F = 75% Complete) | Status (Delivered = D = 100% Complete = fill field with GREEN) | Status (Problem = P = fill field with RED) | Description of problem and solution | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27
DAY 1 | [12 empty] | DUE
Ideation and Planning | High Concept Document | [5 empty] | D | [5 empty] | DUE
| plan.md | [5 empty] | D | [5 empty] | DUE
| readme.md | [5 empty] | D | [5 empty] | DUE
| requirments.txt | [5 empty] | D | [5 empty] | DUE
| refinements-changes.md | [5 empty] | D | [5 empty] | DUE
| plan scripts | [5 empty] | D | [5 empty] | DUE
| prepare concept images for modeling | [5 empty] | D | [5 empty] | DUE
| setup GitHub and Unity Project Folder | [5 empty] | D | [5 empty] | DUE
DUE
DAY 2 | [12 empty] | DUE
Prototype Build | Generate and Import Scripts and attach to required game objects (Cursor AI) | Fallback strategy - other AI tools like Grok and ChatGPT/Codex |  |  |  |  | D | [5 empty] | DUE
| Model Assets and import into unity | Fallback strategy - Unity Asset Store |  |  |  |  | D | [5 empty] | DUE
| Build game environment | [5 empty] | D
| Generate UI | [5 empty] | D | [5 empty] | DUE
| Implement UI in MainMenu, set up working UI | [5 empty] | D | [5 empty] | DUE
| Implement UI in Gameplay scene, set up working UI | [5 empty] | D | [5 empty] | DUE
| Implement UI in PauseMenu, set up working UI | [5 empty] | D | [5 empty] | DUE
| Implement UI in Win Screen, set up working UI | [5 empty] | D | [5 empty] | DUE
| Implement UI in GameOver Screen, set up working UI | [5 empty] | D | [5 empty] | DUE
| Test Game and Debug | [5 empty] | D
| Video demonstartion | show gameplay and narrate design choices, highlighting AI contribution (2-5min) |  |  |  |  | D | [5 empty] | DUE
DUE
DAY 3 | [12 empty] | DUE
Refinements & Submission | Referencing | [5 empty] | D | [5 empty] | DUE
| Testing & Debugging | [5 empty] | D
| Polish Prototype | Add missing UI (retry and main menu button), fix droid orientation, adjust droid behaviour |  |  |  |  | D
| Playable Build | [5 empty] | D | [5 empty] | DUE
| Git repository | all files, commits, and documentation |  |  |  |  | D | [5 empty] | DUE
| Final showcase | Demonnstrate improvements and discuss AI-informed refinements (2-5min) |  |  |  |  | D | [5 empty] | DUE
| Reflection Prompts: short reflections (≈ 200 words each) at the end of plan.md or readme.md. | Where did AI excel, and where did it mislead or limit you? How did AI alter your creative or technical process? What would you change about your collaboration with AI next time? Ethical considerations: Did your use of AI respect originality, transparency, and fair use? Did you credit AI-generated assets appropriately? Were there moments were relying on AI felt ethically questionable? How can you ensure your future work with AI remains responsible and authentic? |  |  |  |  | D
| AI Ethics Statement in readme.md | summarise compliance with originality and fair use |  |  |  |  | D